## Sheet3
Sum of Week | Sum of PV | Sum of EV | Sum of AC
15 | 15000000 | 1200000 | 1465000

## Sheet1
Metric | Value | Status | Week | PV | EV | AC
Project Name | Voting System |  | 1 | 1000000 | 80000 | 90000
Project Manager | Mahek Mulla |  | 2 | 2000000 | 160000 | 185000
Reporting Date |  |  | 3 | 3000000 | 240000 | 280000
|  |  | 4 | 4000000 | 320000 | 390000
% Complete (EV/BAC) | 56% | Blue | 5 | 5000000 | 400000 | 520000
Schedule Performance Index(SPI) | 0.7 | Green
Cost Performance Index(CPI) | 0.86 | Red
Budget at Completion(BAC) | 1,00,00,000 rupees
Estimate at Completion(EAC) | 1,27,50,000 rupees